## Sheet1
Deployment Process Task
S.no	Description	Assigned to	Status	Note	Version
1	Github – API Dll	Ramalakshmi	Completed
1	User Credential - Github username and password update – Design	Dinesh	Completed		Phase I
2	User Credential - Github username and password update – Service	Dinesh
3	Client Credential - Machine/cloud credential update – Design	Dinesh	Completed		Phase I
4	Client Credential – Machine/cloud credential update – Service	Dinesh
5	Build – App_source Category – Design	Muthu	Completed		Phase I
6	Build – App_source Category – Services	Muthu	Completed		Phase I
5	Create Application Window - GITHUB - Repository creation	Dinesh	Completed	Not yet Released	Phase I
14	Build – DDL and DML Script changes – Editor Creation	Muthu	Inprocess		Phase I
6	Create Application – Docker Container creation process for DEP_CAS	Dinesh	Not yet started	Design to finalize	Phase I
7	DEV_CAS - Container Creation process	Dinesh	Not yet started	Design to finalize	Phase I
8	Docker Container creation process – Backend API	Ramalakshmi	Inprocess	Need to finalize API Concept	Phase I
9	Docker File Creation process – Linux SH File and DOCKERFile	Solomon	Inprocess		Phase I
10	DEP_CAS – Designer Insert – Document work	Muthu	Inprocess		Phase I
11	Config Cassandra for Applications	Ramalakshmi	Inprocess	1) Cassandra Keyspace Configuration / 2) Static Table Configuration / 3) Dynamic Mapping XML Configuration / 4) Solr Configuration / 5) Resource File Configuration	Phase I
12	NGINIX Configuration for applications	Ramalakshmi	Inprocess		Phase I
15	Build – DDL and DML Script Changes – API	Ramalakshmi	Not yet started		Phase I
16	Precompiler Utilty Merging	Saranya and Shanthi	Not yet started		Phase I
17	Script Generator Utility process	Saranya	Not yet started		Phase I
18	DEP_CAS – DDL Script maintenance for build - TRN DB tables		Not yet started	No DML Script for DEP_CAS	Phase I
19	DEP_CAS - Reverse scripts should be maintained for rollback contexts		Not yet started		Phase I
13	Platform Containers				Phase II